## Slide 1
ALPHA MANUFACTURING GROUP
AMG ERP Transformation Strategy
Fixing Margin Loss and Protecting Operations
Prepared for: AMG Board of Directors
Presented by: Consultant, Leonard Yaw Mensah
Target Go-Live: Exactly 12 Months From Now
1

## Slide 2
The Core Problem Plaguing AMG
Broken Systems Are Hiding Financial Losses
80%
of custom machinery orders experienced margin losses last year due to tracking errors.
CURRENT CHALLENGES
Fragmented systems across departments
Delayed engineering and BOM synchronization
Heavy dependence on Excel sheets (manual, complex calculations.)
Limited visibility into project costs and profitability
2

## Slide 3
The 12-Month Implementation Roadmap
A Step-by-Step Practical Blueprint (No High-Risk 'Big Bang' Launch)
Phase 1
Months 1–3
Clean & Align
Match operational daily habits to the standard setup of the new software.
Clean out the 20-year-old database and extract only active, current records.
Phase 2
Months 4–8
Build & Connect
Set up the database for our US and Canadian branches.
Build and test the automated link between engineering software and the new ERP.
Integrate core aftermarket parts tracking.
Phase 3
Months 9–11
Test & Train
Have top workers test the new system using old project files for math accuracy.
They then train the rest of the staff.
Phase 4
Month 12
Launch & Support
Freeze the old system over a weekend to move final numbers.
Go-live; keep experts on-site at all 5 factories for 30 days to fix issues instantly.
3

## Slide 4
Key Risks and How We Will Control Them
Keeping the Project on Track and the Factory Floors Running
1
Engineering Sync Failures
Custom part lists transferring incorrectly from designers to the factory floor and other relevant departments, causing building delays.
Mitigation: Set up an automatic validation gate that blocks broken designs before they reach the shop floor.
2
Employees Sticking to Old Spreadsheets
Staff rejecting the new ERP and secretly continuing to run the company out of personal spreadsheets.
Mitigation: Provide thorough team training, build simple dashboards that look like their old tools, and mandate that untracked jobs will not be paid.
3
Cross-Border Accounting Friction
Math errors or delays when calculating US/Canadian dollar conversions and local taxes.
Mitigation: Bring in external cross-border tax experts during Phase 1 to double-check the system's tax rules.
4
Scope Creep and Rising Costs
Department heads demanding unique software customizations that delay the 12-month launch and blow past the budget.
Mitigation: Enforce a strict 'Fit-to-Standard' rule — we change our operational habits to match the software. A governance committee must reject all custom requests unless legally required.
4

## Slide 5
Day-1 Project Scope
Grounded, Realistic Boundaries to Ensure a Safe 12-Month Launch
CRITICAL FOR DAY 1 (IN-SCOPE)
DEFERRED FOR LATER (OUT-OF-SCOPE)
✓
Cross-Border Accounting: Basic bookkeeping that automatically calculates USD/CAD conversions and local taxes.
✓
Job Costing Sub-Ledger: Giving every custom order a unique ID to track live material and labor spending, stopping margin losses instantly.
✓
Live Engineering Link: Automatically sending BOM lists and ECNs from engineering design tools into the production system.
✓
Basic Buying & Inventory Tracking: Simple tracking of raw materials (like steel) and automatic alerts when stocks run low.
✓
Manual Shop Tablets: Rugged touchscreens where workers tap 'Start' and 'Finish' to track labor hours.
→
Automated Machine Tracking (IoT): Connecting factory floor physical welding or cutting tools directly to the database.
→
Advanced Warehouse Tracking: Using 3D shelf-mapping or RFID chips to track the location of individual bolts.
→
Deep Sales Sync: Automated tracking of minor sales emails and conversations inside the ERP database.
→
Customer Tracking Portals: Building a custom tracking website where clients can log in to view their order progress.
→
HR & Payroll Processing: Calculating employee taxes, benefits, and printing paychecks inside the ERP.
Data Migration Trade-Off: We will explicitly exclude individual past invoices, timesheets, and closed project lines from the migration. Day 1 will only load active master files (current customers, active suppliers, current part catalogs) and open balances (unpaid invoices, open orders, and physical warehouse stock).
5

## Slide 6
Data Continuity & Financial Reporting
Protecting Executive Insights Without Slowing Down the New ERP System
Legacy ERP
20-Yr History
Data Lake Archive
e.g., S3 Glacier
New Live ERP
Active Operations
Power BI
Reporting Layer
5-Year Trend & Comparison Reports
→
→
MONTH-END CONTINUITY PLAN
1
Launch lands precisely on Day 1 of a new fiscal month — never mid-close.
2
The prior month closes entirely inside the old system; final numbers become the new ERP's opening baseline.
3
Finance runs weekly practice closes for the first 30 days to catch cross-border currency errors early.
6

## Slide 7
Adopting this Phased Implementation Strategy Would Ensure…
1
Operational Continuity Secured — Zero factory line stoppages during launch due to dedicated, on-site hypercare engineering presence across all 5 international sites.
2
Immediate Financial Recovery — Live, unique project IDs stop margin erosion completely while machinery orders are actively being configured and assembled. Integrating the aftermarket business preserves our highest-margin operation and ensures long-term customer satisfaction.
3
Long-Term Organizational Discipline — Replacing custom legacy adjustments with clean, industry-standard workflows creates an optimized corporate foundation ready for future growth.
Recommendation: Approve the 12-month phased implementation roadmap to immediately protect AMG's core business margins, streamline engineering data flows, and secure upcoming fiscal revenue operations.
7

## Slide 8
FINAL RECOMMENDATION
Conclusion & Expected Business Results
Phased ERP Transformation Strategy
Operational Continuity
Engineering Integration
Trusted Data
Controlled Execution
EXPECTED RESULT
A scalable digital foundation that improves decision-making and supports future growth.
8
Notes: In conclusion, our recommendation provides AMG with the strongest balance between modernization and risk management. By focusing on the foundations first, AMG can achieve ERP transformation without compromising ongoing operations.